## Answer SheetA
General Problems(A)(Answer Sheet)
| Work item | Work detail | Required work volume |  | Unit work volume |  | Required work volume |  | Plan | X Month | [6 empty] | Progress(%)
|  |  | (Amt) | Unit | Human power/machinary/category |  | (Amt) | Man-hours/Machine-hours |  | 1 | 2 | 3 | 4 | 5 | 6 | 7
Actual | bar: X Month 6 to X Month 7
[5 empty] | (Amt) | Unit | (Amt) | Man-days |  | Mon | Tue | Wed | Thu | Fri | Sat | Sun
1 | bar: X Month 6 to X Month 7
2 | bar: X Month 6 to X Month 7
3 | bar: X Month 6 to X Month 7
4 | bar: X Month 6 to X Month 7
5 | bar: X Month 6 to X Month 7
6 | bar: X Month 6 to X Month 7
7 | bar: X Month 6 to X Month 7
8 | bar: X Month 6 to X Month 7
9 | bar: X Month 6 to X Month 7
| Total | [6 empty] | Man-days
| Work volume（Man-days） |  |  |  | Daily work volume（Man-days） |  |  |  | Plan
Modification
Actual
[5 empty] | Cumulative work volume（Man-days） |  |  |  | Plan
Modification
Actual
| Work percentage(%) |  |  |  | Daily work progress percentage(%) |  |  |  | Plan
Modification
Actual
[5 empty] | Cumulative work progress percentage(%) |  |  |  | Plan
Modification
Actual